## Pipeline
Title | Description | New Contract Reference | Value | Value Range (Hide in Reports) | Category | Service Area | Directorate | PLANNED Advert Dispatch Date | PLANNED Tender Return Date | PLANNED Award Date | PLANNED Contract Start
High Level Street Design Feasibility Software | Procurement of an intuitive, existing software tool that will enable policy staff and decision-makers as well as engineers to propose and explore different options for allocating roadspace. - Client to vary the end date as 2 extensions are available. | CA1559 | 70000 | 50K-100K | Digital & Technology | Place & Environment Policy | Transport Policy & Delivery | 2022-12-01 | 2023-01-01 | 2023-03-01 | 2025-02-01
NEC Project Manager for Huddersfield Bus Stations | NEC PM for delivery stage - RIBA 5 / 6 |  | 125000 | 100K-500K | Professional Services | Mobility Services | Transport Ops & Passenger Experience | 2023-05-03 | 2023-06-03 | 2023-06-03 | 2023-06-03
Small Electric Buses | Procurement of 40 small electric buses with different seating configurations. |  | 5000000 | 5M-10M | Fleet | Mobility Services | Transport Ops & Passenger Experience | 2023-06-30 | 2023-07-21 | 2023-08-25 | 2023-09-01
Adult skills marketing campaign |  | n/a | 400000 | 100K-500K | Professional Services | Marketing & Campaigns | Strategy, Comms. & Intelligence | 2023-08-01 | 2023-09-01 | 2023-11-01 | 2023-07-01
Commercial support for the IZ programme | External Commercial (property, QS etc) support for the Investment Zone programme |  | 80000 | 50K-100K | Professional Services | Place & Environment Policy | Policing, Environment & Place | 2023-10-01 | 2023-11-01 | 2024-01-01 | 2024-02-01
Victim Support service/s | Referral, Assessment and Local Support Services for WY |  | 1300000 | 1M-5M | Professional Services | Policing & Crime | Policing, Environment & Place | 2023-10-22 | 2023-11-22 | 2024-01-22 | 2024-11-28
Property Services Cleaning, Customer Care and Posting of Bus Timetables |  | CA1226 | 2075000.34 | 1M-5M | Facilities Management | Facilities & Assets | Transport Ops & Passenger Experience | 2023-11-30 | 2023-12-31 | 2024-02-28
Car share/Car Club | West Yorkshire and York Car Share Contract for Local Authorities | CA1585 / 53568 | 2500000 | 1M-5M | Transport | Transport Policy | Transport Policy & Delivery | 2024-04-01 | 2024-05-01 | 2024-07-01 | 2026-07-01
Automatic Doors: Maintenance, Repair and Replacement |  | TBC / CA1259 | 4000000 | 1M-5M | Facilities Management | Facilities & Assets | Transport Ops & Passenger Experience | 2024-04-01 | 2024-06-01 | 2024-08-01
Freight Transport Association Services |  |  | 60000 | 50K-100K | Transport | Mobility Services | Transport Ops & Passenger Experience | 2024-06-01 | 2024-07-01 | 2024-09-01
Strategic Rail Advisor | Strategic Rail Advisor for the Combined Authority’s Rail Team to help direct/steer our work programme around the development of a number of rail strategies. |  | 700000 | 500K-1M | Transport | Transport Policy | Transport Policy & Delivery | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01
M&E Services Contract | M&E Services Contract | CA51855 | 2150000 | 1M-5M | Facilities Management | Facilities & Assets | Transport Ops & Passenger Experience | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01
HealthTech Business Accelerator (IZ) | A supplier to deliver a business accelerator programme across West Yorkshire under the new Investment Zone programme. |  | 4500000 | 1M-5M | Professional Services | Business Innovation Skills & Culture Policy | Inclusive Economy, Skills & Culture | 2024-07-08 | 2024-08-08 | 2024-10-08 | 2024-11-08
Urban Traffic Management Control Monitoring and Evaluation | Consultant for monitoring and evaluation of existing traffic management control programme |  | 79000 | 50K-100K | Professional Services | Transport Policy | Transport Policy & Delivery | 2024-07-20 | 2024-09-20 | 2024-10-20 | 2024-11-20
West Yorkshire Public Survey (Your Views Policing and Crime) | A West Yorkshire wide survey of residents’ views on policing and safety in our neighbourhoods. To understand public satisfaction and confidence in policing in West Yorkshire. To provide consistent, reliable data of use to WYCA and the Mayor, WYP, and key partners such as CSPs. To provide the public with a meaningful opportunity to shape the work of the above. | RFI- WYCA P&C- West Yorks Residents Survey Procurement reference: 20240418190542-103257 | 300000 |  |  | Policing & Crime | Policing, Environment & Place | 2024-08-15 | 2024-09-15 | 2024-11-15 | 2024-12-01
Economics Advisor | Specialist Economic advice to support development of Mass Transit Business Case |  | 1000000 |  |  | Mass Transit | Mass Transit | 2024-08-15 | 2024-09-15 | 2024-11-15 | 2024-12-01
Consultancy advisor for Mass Transit Phase 2 | Specialist support for development of scope for Mass Transit Phase 2 |  | 1000000 |  |  | Mass Transit | Mass Transit | 2024-08-15 | 2024-09-15 | 2024-11-15 | 2024-12-01
Mass Transit Independent Competent Person | Appoint an 'independent competent person' (ICP) to help devise a written scheme of verification for the Mss Transit system in compliance with statutory requirements |  | 8000000 |  |  | Mass Transit | Mass Transit | 2024-08-15 | 2024-09-15 | 2024-11-15 | 2024-12-01
Provision of Real-Time Passenger Information Battery Powered Displays for Bus Stop Pole and Shelters | Provision of Real-Time Passenger Information Battery Powered Displays for Bus Stop Pole and Shelters | PROJECT CA1088 | 10000000 | 10M-20M | Digital & Technology | Transport Policy | Transport Policy & Delivery | 2024-09-01 | 2024-10-01 | 2024-12-01 | 2025-01-01
Marketing & Communications Framework | Provision of Marketing and Communications Services |  | 2000000 | 1M-5M | Communications | Marketing & Campaigns | Strategy, Comms. & Intelligence | 2024-10-01 | 2024-11-01 | 2025-01-01 | 2022-10-01
Phase 1 Mobility Hub Component Procurement |  |  | 2500000 | 1M-5M | Built Environment | Transport Implementation | Transport Policy & Delivery | 2024-10-01 | 2024-11-01 | 2024-12-15 | 2025-01-01
Bus Reform Technology Partner | In order to manage the risks of the technical implementation of new systems, an external Bus Reform Technology Partner is procured to be available from early 2025. The partner would: 1. Provide independent advice and attend the Data transition Working Board (where required). 2. Deliver specific technical products where it is determined to be the best approach. This could be because of a lack of internal capacity, unavailable in-house skills or because of the likely costs / timescales / fit of procuring commercially off the shelf solutions. |  | 750000 | 500K-1M | Digital & Technology | Digital & Technology Services | Corporate Centre | 2024-10-03 | 2024-11-09 | 2024-12-16 | 2024-01-15
Gas | Gas Supply |  | 300000 | 100K-500K | Facilities Management | Facilities & Assets | Transport Ops & Passenger Experience | 2025-01-01 | 2025-02-01 | 2025-04-01 | 2025-05-01
Skills Bootcamps Wave 6 provision | Adult skills training courses for West Yorkshire residents | N/A | 6000000 |  |  | Employment & Skills | Inclusive Economy, Skills & Culture | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01
Wide Area Network | Wide Area Network | PROJECT CA1230 |  | 30K-50K | Services | Digital & Technology Services | Corporate Centre | 2025-01-01 | 2025-02-01 | 2025-04-01 | 2025-05-01
Smartcard Production 2021 | West Yorkshire Combined Authority is looking to appoint a Single Supplier Framework Provider for the production of ENCTS and MCard Smartcards including letter production and direct customer mailing, and batch card production. | CA1498 | 880000 | 500K-1M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2025-04-18 | 2025-05-18 | 2025-07-18 | 2026-05-12
Printing and Distribution of Bus Timetables | Printing and distribution of individual timetables for West Yorkshire buses |  | 180000 | 100K-500K | Transport | Passenger Experience | Transport Ops & Passenger Experience | 2025-06-01 | 2025-07-01 | 2025-09-01 | 2025-10-31
Bus Franchising - Round 1 - Zone/Lot 1 B | Leeds 3 Small Lot (Total Leeds 3 Peak Vehicle Requirement = 103). |  | 5000000 | 5M-10M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2025-10-01 |  | 2025-12-31 | 2026-04-01
Bus Franchising - Round 1 - Zone/Lot 1 A | Leeds 3 Large Lot (Total Leeds 3 Peak Vehicle Requirement = 103). |  | 15000000 | 10M-20M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2025-10-01 | 2025-12-01 | 2026-06-30 | 2027-04-01
Bus Franchising - Round 1 - Zone/Lot 2A | Heavy Woolen Large Lot (Total Heavy Woolen Peak Vehicle Requirement = 89). |  | 15000000 | 10M-20M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2025-10-01 |  | 2026-06-30 | 2027-04-01
Bus Franchising - Round 1 - Zone/Lot 3A | Kirklees Large Lot (Peak Vehicle Requirement = 75). |  | 15000000 | 10M-20M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2025-10-01 |  | 2026-06-30 | 2027-04-01
Temporary Staffing and Hard to Fill Recruitment Vacancies |  |  | 3000000 | 1M-5M | Professional Services | HR | Corporate Centre | 2025-12-01 | 2026-01-01 | 2026-03-01 | 2026-04-01
Electricity Supply | Electricity Supply |  | 10000000 | 10M-20M | Facilities Management | Facilities & Assets | Transport Ops & Passenger Experience | 2026-01-01 | 2026-02-01 | 2026-04-01 | 2026-05-01
Franchising - Round 1 - Zone/Lot 2B | Heavy Woolen Small Lot (Total Heavy Woolen Peak Vehicle Requirement = 89). |  | 5000000 | 5M-10M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2026-04-01 |  | 2026-06-30 | 2027-10-01
Digital Skills Framework | Setting up a multiple supplier framework in order to train individuals in digital skills across West Yorkshire. | 53161 | 30000000 | 20M+ | Professional Services | Employment & Skills | Inclusive Economy, Skills & Culture | 2026-05-01 | 2026-06-01 | 2026-08-01 | 2026-10-01
Franchising - Round 2 - Zone/Lot 1B | Wakefield Small Lot (Total Wakefield Peak Vehicle Requirement = 77). |  | 5000000 | 5M-10M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2026-07-01 |  | 2027-09-30 | 2027-01-01
Franchising - Round 2 - Zone/Lot 1A | Wakefield Large Lot (Total Wakefield Peak Vehicle Requirement = 77). |  | 15000000 | 10M-20M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2026-07-01 |  | 2027-03-31 | 2028-01-01
Franchising - Round 2 - Zone/Lot 2A | Leeds 1 Large Lot (Total Leeds 1 Peak Vehicle Requirement = 70). |  | 15000000 | 10M-20M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2026-07-01 |  | 2027-03-31 | 2028-01-01
Franchising - Round 2 - Zone/Lot 3A | Five Towns Large Lot (Total Five Towns Peak Vehicle Requirement = 49). |  | 15000000 | 10M-20M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2026-07-01 |  | 2027-03-31 | 2028-01-01
Franchising - Round 1 - Zone/Lot 3B | Kirklees Small Lot (Peak Vehicle Requirement = 75). |  | 5000000 | 5M-10M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2026-10-01 |  | 2026-12-31 | 2027-04-01
Franchising - Round 2 - Zone/Lot 2B | Leeds 1 Small Lot (Total Leeds 1 Peak Vehicle Requirement = 70). |  | 5000000 | 5M-10M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-01-01 |  | 2027-03-31 | 2028-07-01
Franchising - Round 3 - Zone/Lot 1B | Bradford Small Lot (Total Bradford Peak Vehicle Requirement = 171) |  | 5000000 | 5M-10M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-04-01 |  | 2027-06-30 | 2027-10-01
Franchising - Round 3 - Zone/Lot 2B | Keighley Small Lot (Total Keighley Peak Vehicle Requirement = 101) |  | 5000000 | 5M-10M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-04-01 |  | 2027-06-30 | 2027-10-01
Franchising - Round 3 - Zone/Lot 1A | Bradford Large Lot (Total Bradford Peak Vehicle Requirement = 171) |  | 15000000 | 10M-20M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-04-01 |  | 2027-12-30 | 2028-10-01
Franchising - Round 3 - Zone/Lot 2A | Keighley Large Lot (Total Keighley Peak Vehicle Requirement = 101) |  | 15000000 | 10M-20M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-04-01 |  | 2027-12-30 | 2028-10-01
Franchising - Round 3 - Zone/Lot 3A | Leeds 2 Large Lot (Total Leeds 2 Peak Vehicle Requirement = 91) |  | 15000000 | 10M-20M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-04-01 |  | 2027-12-30 | 2028-10-01
Franchising - Round 3 - Zone/Lot 4A | Calderdale Large Lot (Total Calderdale Peak Vehicle Requirement = 67) |  | 15000000 | 10M-20M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-04-01 |  | 2027-12-30 | 2028-10-01
Franchising - Round 2 - Zone/Lot 3B | Five Towns Small Lot (Total Five Towns Peak Vehicle Requirement = 49). |  | 5000000 | 5M-10M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-07-01 |  | 2027-10-31 | 2028-01-01
Franchising - Round 3 - Zone/Lot 3B | Leeds 2 Small Lot (Total Leeds 2 Peak Vehicle Requirement = 91) |  | 5000000 | 5M-10M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-10-01 |  | 2027-12-30 | 2028-04-01
Franchising - Round 3 - Zone/Lot 4B | Calderdale Small Lot (Total Calderdale Peak Vehicle Requirement = 67) |  | 5000000 | 5M-10M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2028-04-01 |  | 2027-12-30 | 2028-10-01
Further Education Course Providers for Adult Education Budget (DPS Stage 1) |  | CA1310 | 20000000 | 20M+ | Professional Services | Employment & Skills | Inclusive Economy, Skills & Culture | 2028-04-01 | 2028-05-01 | 2028-07-01 | 2028-08-01
Real Time Information System | Provision of an Advanced Yorkshire & Humber Real Time Information System and associated services to the Combined Authority (the Services) | PROJECT CA1429 | 841000 | 500K-1M | Digital & Technology | Digital & Technology Services | Corporate Centre | 2031-09-01 | 2031-10-01 | 2031-12-01 | 2032-01-01
Huddersfield Bus Station Building Control Principal Designer |  |  | 60000 | 50K-100K | Professional Services | Transport Implementation | Transport Policy & Delivery |  |  |  | 2025-02-01
Project Evaluation |  | n/a | 60000 | 50K-100K |  |  | Inclusive Economy, Skills & Culture
Tendered Bus Services Expiring August 2025 | Various tendered bus services requiring extension and/or re-tender. See comments before allocation. | N/A | 60000 | 50K-100K | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2025-09-01
Access Bus Service Review Support | Requirement for consultancy support to conduct review of Access Bus Service - fit for purpose etc. Teams internally approached but no capacity available so external support required. Report from consultant required by end of June 2024 |  | 75000 | 50K-100K | Professional Services | Mobility Services | Transport Ops & Passenger Experience
CO2 impact evaluation scoping study |  |  | 80000 | 50K-100K | Professional Services | Research & Intelligence | Strategy, Comms. & Intelligence |  |  |  | 2024-10-01
Corporate Environmental Plan |  |  | 100000 | 100K-500K | Professional Services | Strategy & Corporate Performance | Transport Policy & Delivery |  |  |  | 2025-02-01
Enterprise Model Finalisation Consultancy Support for Mass Transit | Refined Enterprise model and Capability model that integrates with Bus Reform and outlines the Transition Management Plan for capability development. |  | 110000 | 100K-500K | Professional Services | Mass Transit | Mass Transit
Organisational Development Consultancy Support for Mass Transit | Capability development and refinement of the Programme Structure for WYMT. |  | 120000 | 100K-500K | Professional Services | Mass Transit | Mass Transit
Social Media Management Tool |  | n/a | 150000 | 100K-500K | Digital & Technology | Media | Strategy, Comms. & Intelligence |  |  |  | 2024-04-01
Local Transport Plan - Statutory Consultation Support | TBC |  | 150000 | 100K-500K | Professional Services | Economic Implementation | Transport Policy & Delivery |  |  |  | 2025-02-01
Tendered Bus Services Expiring April 2026 | Various tendered bus services requiring extension and/or re-tender. See comments before allocation. | N/A | 150000 | 100K-500K | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2026-05-01
Mobile Phone Replacements | Awaiting for final budget approval The replacement of 350 corporate mobile phones with more modern devices. |  | 150000 | 100K-500K | Digital & Technology | Digital & Technology Services | Corporate Centre
Meeting Room Improvements | Awaiting for final budget approval Improve the collaborative experience and ease of use of office hybrid meeting rooms. Potentially improving cameras so that remote participants can view more of the meeting room environment. |  | 150000 | 100K-500K | Digital & Technology | Digital & Technology Services | Corporate Centre
Tendered Bus Services Expiring March 2025 | Various tendered bus services requiring extension and/or re-tender. See comments before allocation. | N/A | 240000 | 100K-500K | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2025-04-01
Waste Disposal - Wellington House and Bus Stations | Provision of waste management services. | CA1459 | 330000 | 100K-500K | Facilities Management | Facilities & Assets | Transport Ops & Passenger Experience
Development fund for the Growth Service |  |  | 350000 | 100K-500K | Services | Business Innovation Skills & Culture Policy | Inclusive Economy, Skills & Culture |  |  |  | 2025-03-01
Laptop Refresh | Awaiting for final budget approval Replacement of approximately 450 devices issued to WYCA employees which are coming to end of service life (5 years) |  | 400000 | 100K-500K | Digital & Technology | Digital & Technology Services | Corporate Centre
Tendered Bus Services Expiring October 2024 | Various tendered bus services requiring extension and/or re-tender. See comments before allocation. | N/A | 450000 | 100K-500K | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2024-11-01
Business Improvement call-off resource |  |  | 500000 | 500K-1M | Services | Strategy & Corporate Performance | Strategy, Comms. & Intelligence |  |  |  | 2023-11-05
Professional Services Framework | Professional Services Framework to provide generic business case development including external expertise and consultancy to complete business cases. |  | 500000 | 500K-1M | Professional Services | Economic Implementation | Inclusive Economy, Skills & Culture
Research and Intelligence Framework |  |  | 500000 | 500K-1M | Digital & Technology | Research & Intelligence | Strategy, Comms. & Intelligence
CSM Assessor | Common Safety Method (CSM) support to develop and deliver proposals for a new rail station at Elland, Leeds Bradford, White Rose and Thorpe Park). |  | 552503.66 | 500K-1M | Professional Services | Transport Implementation | Transport Policy & Delivery
Tendered Bus Services Expiring January 2026 | Various tendered bus services requiring extension and/or re-tender. See comments before allocation. | N/A | 600000 | 500K-1M | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2026-02-01
West Yorkshire Investment Zone - External Legal Advice | External legal advice | Not applicable | 600000 |  |  | Economic Implementation | Policing, Environment & Place |  |  |  | 2024-09-01
Mass Transit Accessibility Consultant | To procure the services of an Accessibility Consultant to assist with a number of aspects of Mass Transit development | 81781 | 625000 | 500K-1M | Professional Services | Transport Policy | Mass Transit |  |  | 2023-01-03
Tendered Bus Services Expiring May 2025 | Various tendered bus services requiring extension and/or re-tender. See comments before allocation. | N/A | 850000 | 500K-1M | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2025-06-01
ICT Consultancy Framework | Provision of a framework for consultants to provide pre tender support including proof of concepts, options appraisals and supporting specification writing. |  | 1000000 | 1M-5M | Digital & Technology | Digital & Technology Services | Corporate Centre |  |  |  | 2024-08-01
Skills Bootcamps - Wave 5 midyear provision | Not a repeated procurement however will be very similar to previous procurement exercises delivered under Skills Bootcamp programme |  | 1100000 | 1M-5M | Services | Employment & Skills | Inclusive Economy, Skills & Culture |  |  |  | 2024-04-01
Tendered Bus Services Expiring September 2024 | Various tendered bus services requiring extension and/or re-tender. See comments before allocation. | N/A | 1100000 | 1M-5M | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2024-10-01
Tendered Bus Services Expiring September 2026 | Various tendered bus services requiring extension and/or re-tender. See comments before allocation. | N/A | 1100000 | 1M-5M | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2026-10-01
Tendered Bus Services Expiring October 2025 | Various tendered bus services requiring extension and/or re-tender. See comments before allocation. | N/A | 1300000 | 1M-5M | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2025-11-01
Tendered Bus Services Expiring February 2025 | Various tendered bus services requiring extension and/or re-tender. See comments before allocation. | N/A | 1600000 | 1M-5M | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2025-03-01
LBAP Rail Station - Ground Investigation, Detailed Design, FBC & Planning Applications | Consultancy required to complete the initial package of ground investigations, Detailed Design, completion of the FBC & all planning applications. |  | 2400000 | 1M-5M | Civils | Transport Implementation | Transport Policy & Delivery |  |  |  | 2024-08-01
Leeds Bus Station Roof - Works | Leeds Bus Station Roof - Works |  | 2500000 | 1M-5M | Civils | Facilities & Assets | Transport Ops & Passenger Experience |  |  |  | 2024-07-01
Stourton Park and Ride | Provision of Stourton Park and Ride Electric Bus service |  | 3500000 | 1M-5M | Transport | Mobility Services | Transport Ops & Passenger Experience
Tendered Bus Services Expiring July 2025 | Various tendered bus services requiring extension and/or re-tender. See comments before allocation. | N/A | 3900000 | 1M-5M | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2025-08-01
School Bus and Swimming Contracts ending on 31 December 2024 | School Transport services for re-tendering. Commencement of services 01/01/25 | N/A | 4700000 | 1M-5M | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2025-01-02
School Bus Contracts ending on 31 August 2025 | School Transport services for re-tendering. Commencement of services 01/09/25 | N/A | 8400000 | 5M-10M | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2025-09-01
Adult Skills Training Framework (formally reboot) |  | CA1421 | 30000000 | 20M+ | Professional Services | Employment & Skills | Inclusive Economy, Skills & Culture
Universal Support (Work and Health) |  | n/a | 42600000 | 20M+ | Services | Employment & Skills | Inclusive Economy, Skills & Culture |  |  |  | 2024-09-02
Thorpe Park (residential) |  | N/A | 50000000 | 20M+ | Built Environment | Economic Implementation | Policing, Environment & Place |  |  |  | 2025-10-01
LBA Parkway Rail Station - GRIP 5-8 Contractor | Construction of LBAP rail station |  | 60000000 | 20M+ | Civils | Transport Implementation | Transport Policy & Delivery |  |  |  | 2025-02-01
Mass Transit Delivery Packages | Mass Transit Construction | N/A | 1911760000 | 20M+ | Built Environment | Mass Transit | Mass Transit |  |  |  | 2028-11-01
Operating System Upgrade | Awaiting for final budget approval The upgrade of corporate laptops to Windows 11 to ensure compliance with latest security patches and improved performance. |  |  | 30K-50K | Digital & Technology | Digital & Technology Services | Corporate Centre
Wide Area Network (WAN) Refresh | Awaiting for final budget approval Requirement to refresh the WAN (over 9 years old) based on changing business needs and technology enhancements. |  |  | 30K-50K | Digital & Technology | Digital & Technology Services | Corporate Centre
Cloud Configuration Updates | Awaiting for final budget approval Implement tighter security configurations on cloud services to improve security and lower maintenance |  |  | 30K-50K | Digital & Technology | Digital & Technology Services | Corporate Centre
Wi-Fi Coverage at Bus Stations | Awaiting for final budget approval Wi-Fi Coverage at Bus Stations - Upgrade and extend Wi-Fi capability at Bus stations to meet the needs of site-based employees who require access to central applications or employees attending site to carry out Health and Safety tasks (e.g. surveys, onsite/on the spot incidents). |  |  | 30K-50K | Digital & Technology | Digital & Technology Services | Corporate Centre
Wellington House – Power Supply Improvement | Awaiting for final budget approval Improve the power arrangements at Wellington House so that in the event of a power outage, contingency arrangements enable the server room and comms equipment to keep functioning. |  |  | 30K-50K | Digital & Technology | Digital & Technology Services | Corporate Centre
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please amend to 60 Characters or less when transferring from previous tab

## WIP
Title | Description | New Contract Reference | Value | Value Range (Hide in Reports) | Category | Service | Directorate | PLANNED Advert Dispatch Date | PLANNED Tender Return Date | PLANNED Award Date | PLANNED Contract Start | ACTUAL Advert Dispatch Date | ACTUAL Tender Return Date | ACTUAL Award Date | ACTUAL Contract Start
Evaluation Framework | Framework agreement to meet future varying needs of evaluation team with efficient call off mechanism. | 82980 | 6500000 | 5M-10M | Professional Services | Research & Intelligence | Corporate Centre | 2024-04-24 | 2024-06-07 | 2024-07-29 | 2024-08-05 | 2024-04-24
Bus Reform Depot and Land Surveys | Procurement of consultants to survey current & potential future depots or land. | 86673 | 250000 | 100K-500K | Professional Services | Bus Reform | Transport Policy & Delivery | 2024-05-13 | 2024-06-12 | 2024-07-16 | 2024-08-01
Bus Franchising Professional Services Support | Procurement of consultancy services to support Network Management & Planning, Assets, and Contracting workstreams. |  | 2500000 | 1M-5M | Professional Services | Bus Reform | Transport Policy & Delivery | 2024-04-29 | 2024-06-12 | 2024-07-15 | 2024-07-22 | 2024-04-29
Data Partner for Data Platform |  |  | 150000 | 100K-500K | Digital & Technology | Digital & Technology Services | Corporate Centre | 2024-05-17 | 2024-06-17 | 2024-07-15 | 2024-07-19 | 2023-08-17 | 2023-09-20 | 2023-12-18 | 2023-01-15
Evaluation of the Domestic Net Zero Programme | Consultancy support is required to undertake a number of evaluation tasks that will both guide later starting aspects to the programme and report on the programme delivery to term. | 84180 | 200000 | 100K-500K | Professional Services | Place & Environment Policy | Policing, Environment & Place | 2024-06-19 | 2024-06-19 | 2024-08-09 | 2024-09-01
School Transport Contracts Ending 31 August 2024 | Leisure and School bus contracts to be tendered for current contracts ending August 24 | 87487 | 6400000 | 5M-10M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2024-05-17 | 2024-06-19 | 2024-07-29 | 2024-09-01 | 2024-05-17
West Yorkshire LTP - External Transport Consultancy Support | Support from consultant specialising in Transport is needed to support the second phase of the Local Transport Plan to ensure that this statutory document is ready for adoption to support the delivery of the CA’s key strategic transport programmes Mass transit and Bus Reform. Additional consultancy support in Transport is needed for transport policy and strategy development relating both to the LTP adoption and post LTP delivery. Commercial support is required to set up a new framework given the estimated value and specialist nature of the service required. | 84529 | 1100000 | 1M-5M |  | Transport Policy | Transport Policy & Delivery | 2024-05-31 | 2024-06-21 | 2024-07-12 | 2024-08-01 | 2024-05-31 | 2024-06-21 | 2024-07-12 | 2024-08-01
SEN Taxis DPS Call off | Call off from CA's SEN Transport DPS (64800) | 87879 | 4060000 | 1M-5M | Transport | Mobility Services | Transport Ops & Passenger Experience | 2024-06-07 | 2024-06-24 | 2024-06-28 | 2024-09-02
Building Fabric Maintenance and Repair Contract | Building Fabric Maintenance and Repair Contract | 81450 | 5000000 | 5M-10M | Facilities Management | Facilities & Assets | Transport Ops & Passenger Experience | 2024-05-31 | 2024-07-01 | 2024-08-02 | 2024-09-01
Property and Estates Management Services | Estate management service relating to portfolio of properties, land and assets and located in the five districts of West Yorkshire. |  | 5000000 | 5M-10M | Facilities Management | Facilities & Assets | Transport Ops & Passenger Experience | 2024-06-01 | 2024-07-01 | 2024-08-02 | 2024-09-01 | 2024-07-01 | 2024-08-02 | 2024-09-01
Huddersfield Bus Station Construction | Contract Phase Two incorporating Kirklees Canopy works |  | 14000000 | 10M-20M | Civils | Transforming Cities Fund | Transport Policy & Delivery | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01
IT Sofware & Hardware Partner |  | 81062 | 30000000 | 20M+ | Digital & Technology | Digital & Technology Services | Finance & Commercial Services | 2024-05-31 | 2024-07-01 | 2024-09-05 | 2024-10-01
"You Can Make It Here" programme - Music Network Sector Capacity Building and Export | Supplier to support WY music sector with knowledge sharing activities to support sector growth. | 87602 | 140000 | 100K-500K | Professional Services | Trade & Investment | Inclusive Economy, Skills & Culture | 2024-06-07 | 2024-07-04 | 2024-08-01 | 2024-08-22
ZEB phase 2&3 FBC development |  |  | 60000 | 50K-100K |  | Transforming Cities Fund | Transport Policy & Delivery | 2024-06-07 | 2024-07-07 | 2024-09-07 | 2024-10-29
"You Can Make It Here" programme - Export Accelerator - creative industries | Supplier to support creative industries businesses to diversify revenue, grow new audiences, develop new business models and increase exports |  | 250000 | 100K-500K | Professional Services | Trade & Investment | Inclusive Economy, Skills & Culture | 2024-06-10 | 2024-07-08 | 2024-08-15 | 2024-08-31
Mayors Graduate Pilot | The Mayoral SME Graduate Pilot will provide support with attracting, onboarding and training talent. This, in turn, will address challenges around skills gaps, recruitment, and retention of graduate talent in SMEs. This approach will also provide targeted intervention based on regional sectoral need. The main beneficiaries of the pilot will be the SME community, with local graduates and regional universities being secondary beneficiaries. | 79593 | 400000 | 100K-500K | Professional Services | Employment & Skills | Inclusive Economy, Skills & Culture | 2024-06-24 | 2024-07-24 | 2024-08-14 | 2024-08-26
Regional Heritage Guide | Development of a guide that will ensure consistency and robustness of approach in balancing the needs of retrofit against planning/heritage considerations. | 87382 | 80000 | 50K-100K |  |  | Policing, Environment & Place | 2024-07-01 | 2024-07-26 | 2024-09-09 | 2024-09-23
West Yorkshire District Cordon Count Programme | Conduct annual survey of the number of people using different means of transportation in West Yorkshire to provide required data for planning sustainable travel within the district. | 86641 | 500000 | 500K-1M | Professional Services | Research & Intelligence | Strategy, Comms. & Intelligence | 2024-06-24 | 2024-07-26 | 2024-09-09 | 2024-09-23
Dewsbury Bus Station Construction | Contract Phase Two from 60193 |  | 13920000 | 10M-20M | Civils | Transforming Cities Fund | Transport Policy & Delivery | 2024-06-21 | 2024-07-26 | 2024-07-12
Bradford Council CL responsiveness - procurement on behalf of Bradford Council |  | N/a | 400000 | 100K-500K |  |  | Inclusive Economy, Skills & Culture | 2024-07-01 | 2024-08-01 | 2024-10-01 | 2024-06-24
Digital Workforce for the Future | An inclusive activity to inspire school-aged children to engage with digital literacy/skills/education/careers, link local employers with digital skills delivery, and develop digital literacy networks across education and employers. |  | 750000 | 500K-1M | Professional Services | Employment & Skills | Inclusive Economy, Skills & Culture | 2024-07-05 | 2024-08-05 | 2024-09-26 | 2024-10-17
Mass Transit Environmental Partner 2 | Environmental Partner to support the ongoing Mass Transit Programme |  | 15000000 | 10M-20M | Professional Services | Mass Transit | Mass Transit | 2024-07-17 | 2024-08-16 | 2024-09-10 | 2024-09-23
Business support for Heritage Organisations | Business support and training to help heritage organisations survive and grow |  | 82000 | 50K-100K | Professional Services | Trade & Investment | Inclusive Economy, Skills & Culture | 2024-07-15 | 2024-08-19 | 2024-09-19 | 2024-10-10
Business support for Sports Clubs | Business support and training to help sports clubs survive and grow |  | 82000 | 50K-100K | Professional Services | Trade & Investment | Inclusive Economy, Skills & Culture | 2024-07-15 | 2024-08-19 | 2024-09-19 | 2024-10-10
Urban Traffic Management Control Monitoring and Evaluation | Consultant for monitoring and evaluation of existing traffic management control programme. |  | 79000 | 50K-100K | Professional Services | Transport Policy | Transport Policy & Delivery | 2024-07-20 | 2024-08-20 | 2024-10-20 | 2024-11-20
BuS Management System (CoSA re-procurement) |  | 85504 | 2000000 | 1M-5M | Digital & Technology |  | Transport Ops & Passenger Experience | 2024-07-24 | 2024-08-30 | 2024-10-08 | 2024-11-01
Better Homes Hub - Retrofit One Stop Shop | Better Homes Hub - Retrofit One Stop Shop |  | 500000000 | 20M+ | Professional Services | Place & Environment Policy | Policing, Environment & Place | 2024-08-01 | 2024-09-01 | 2024-10-15 | 2024-11-01
Huddersfield Bus Station FBC Support |  |  | 65000 | 50K-100K |  | Transforming Cities Fund | Transport Policy & Delivery
HDBS Client Side Architectural Support |  |  | 70000 | 50K-100K |  | Transforming Cities Fund | Transport Policy & Delivery
Cargobikes for Hubs | Purchase cargobikes for our newly created active travel hubs |  | 70000 | 50K-100K |  | Marketing & Campaigns | Strategy, Comms. & Intelligence |  |  |  | 2024-06-03
West Yorkshire Bus Network Plan |  | 83220 | 100000 | 100K-500K | Transport | Bus Reform | Transport Policy & Delivery
Penetration Testing Partner |  |  | 100000 | 100K-500K | Digital & Technology |  | Corporate Centre |  |  |  | 2024-06-01
Adult Skills Evaluation |  | 87385 | 100000 | 100K-500K |  |  | Inclusive Economy, Skills & Culture
Levelling Up Fund Round 2 Post Bid Support |  |  | 100000 | 100K-500K | Professional Services | Transforming Cities Fund | Transport Policy & Delivery |  |  |  | 2023-11-01
Digitising Services - Business Change and Improvement | Staff training. |  | 120000 | 100K-500K | Digital & Technology | Digital & Technology Services | Corporate Centre
NEC Project Manager for Dewsbury Bus Stations | NEC PM for delivery stage - RIBA 5 / 6 |  | 125000 | 100K-500K | Professional Services | Transport Implementation | Transport Policy & Delivery
Measuring the impact of BSIP Fares Initiatives |  | 83532 | 145000 | 100K-500K | Professional Services | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2023-08-14
Re-procurement of 365Respone Flexiroute system |  | Contract Reference: 50011 (The CA ref for the software partner is: CA1229) | 180000 | 100K-500K | Digital & Technology | Digital & Technology Services | Corporate Centre |  |  |  | 2024-03-01
Retrofit Coordinator (Better Homes Hub Area-based schemes) |  | TBC | 180000 | 100K-500K | Services | Economic Implementation | Policing, Environment & Place |  |  |  | 2024-06-01
Langthwaite EZ - NEC Site Supervisor |  |  | 180000 | 100K-500K | Professional Services | Economic Implementation | Policing, Environment & Place
West Yorkshire Transport Insights Survey – 2023 to 2025 (tentatively renamed from Transport Recovery Survey) |  |  | 200000 | 100K-500K | Professional Services | Transport Policy | Transport Policy & Delivery
Bradford Interchange Structural Surveys 2 | Structural surveys to ascertain the scope of works needed at Bradford Interchange |  | 300000 | 100K-500K |  |  | Transport Ops & Passenger Experience
Multiply - Community and Family Learning |  |  | 325000 | 100K-500K | Professional Services | Employment & Skills | Inclusive Economy, Skills & Culture |  |  |  | 2024-07-01
Food and Drinks Vending Provision | The Combined Authority are looking to enter into an agreement for the provision, installation, maintenance and de-installation of snacks and soft drink vending machines at our bus stations/sites. | 82679 | 330000 | 100K-500K | Facilities Management | Passenger Experience | Transport Ops & Passenger Experience |  |  | 2024-05-08 |  | 2024-03-20 | 2024-04-18 | 2024-05-21
Redevelopment of Combined Authority Website Presence |  | N/A | 400000 | 100K-500K |  | Media | Strategy, Comms. & Intelligence |  |  |  | 2024-06-03
Travel Booking System | Requirement to establish a compliant contract for a modern easy system to make travel booking within the CA more streamlined. | 81613 | 500000 | 500K-1M | Professional Services | Trade & Investment | Inclusive Economy, Skills & Culture
West Yorkshire Investment Zone - External Legal Advice | External legal advice | Not applicable | 600000 |  |  | Economic Implementation | Policing, Environment & Place |  |  |  | 2024-09-01
LBA Parkway MVP Assessment |  | CA1254 and CA64776 | 1000000 | 1M-5M |  |  | Transport Policy & Delivery |  |  |  | 2024-07-01
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should follow budget holder